## Meeting 1
Meeting 1
Date | Location | Objective | Agenda/Discussion | Decisions | Tasks | Responsible | Deadline
2026-02-03 | Cross Keys | Select paper | Discuss paper & CCU model | Paper selected | Read paper | All
[5 empty] | Summarize methods | Member
[5 empty] | Identify parameters to use in our model | Member

## Meeting 2
Meeting 2
Date | Location | Objective | Agenda/Discussion | Decisions | Tasks | Responsible
13/03/2026 | F19 Room | Understanding the model | Patient flow & distributions | Use Python | Defining of Parameters in our model | Member
[5 empty] | Research distributions | Member
[5 empty] | Sketch out the model flow | Member

## Meeting 3
Meeting 3
Date | Location | Objective | Agenda/Discussion | Decisions | Tasks | Responsible
18/03/2026 | Teams | Build simulation | Implement arrivals & queues | Core model built | Complete code | Member
[5 empty] | Implement queue | Member
[5 empty] | Test outputs | Member

## Meeting 4
Meeting 4
Date | Location | Objective | Agenda/Discussion | Decisions | Tasks | Responsible
22/03/2026 | Teams | Evaluate results | Compare with paper | Include scenarios | Finalize the model | Member
[5 empty] | Write report | All

## Action Plan
Action Plan with Milestones | [8 empty] | Milestone Summary
Milestone ID | Milestone | Related Meeting | Key Deliverable | Action / Next Step | Responsible | Target / Deadline | Status | Notes | Total milestones
M1 | Paper selection and project alignment | Meeting 1 | Agreed paper and project scope | Confirm selected paper and assign full-paper reading | All | Week 1 | Completed | Held at Cross Keys | Completed
M2 | Paper review and variable extraction | Meetings 1-2 | Summary of CCU model inputs and assumptions | Extract arrivals, length of stay, bed-capacity logic, and scenarios | All | Week 1-2 | Completed | Paper uses DES for CCU bed occupancy | Completed
M3 | Model design and software choice | Meeting 2 | Simulation workflow and tool decision | Map queue logic and confirm Python approach | Assigned members | Week 2 | Completed | Held in F19 room | Completed
M4 | Prototype simulation build | Meeting 3 | Initial model with arrivals, beds, and queue rules | Complete base code and run initial tests | Assigned members | Week 3 | Completed | Held on Teams
M5 | Results review and refinement | Meeting 4 | Comparison of model output with paper findings | Validate results and refine assumptions where needed | All | Week 4 | Completed | Held on Teams
M6 | Final report and presentation preparation | Post-meeting follow-up | Submission-ready report | Write final report | All | Before submission | Completed | Final milestone before assessment